| Department | Gedanken Sciences Department (GSD) | Period (Q/FY) | Q3 2017/18 |
| --- | --- | --- | --- |
| Learning from Departmental SHE incidents for others | Several items of science equipment which work under high pressure were purchased without any evidence of proof testing and were installed and commissioned on site without registration for statutory inspection. The need for statutory inspection should be highlighted with science and engineering staff. GSD purchased 6 desk top monitor risers from ABC Monitors, model DR101, one failed in use when the locking catch broke, and the other have been checked. Any others using this model should check their safety. |  |  |
| Significant findings from Department safety tours Progress in completion of actions arising | Safety tours of tenant work areas in GSD buildings highlighted a range of issues including lack of maintenance of fire extinguishers due to the secure nature of these restricted work areas. Consideration should be given as to how fire extinguishers in tenants work areas are managed. Progress in completing actions from GSD safety tours: Tour Ref.; Date; Area; Actions. Complete; In progress; Overdue. GSD/16/02; 2/5/17; Lab 1; 10; 5; 2. GSD/16/02; 5/7/17; Lab 2; 2; 13; 4. GSD/16/02; 23/9/17; Offices G14; 5; 0; 0. GSD/16/02; 24/10/17; Lab 5; 16; 10; 8. |
| Progress with Department SHE Improvement Plans | Progress in GSD 2017/18 SHE Improvement plan: Ref.; Objectives; Progress; Commentary. GSD/01; Complete Safety tour programme; 4 of 6 planned completed, on track to deliver. GSD/02; Refurbish and tidy lab 6 removing hazards and wastes; Complete; Now operational. GSD/03; Ensure all GSD RAs reviewed by 2 year standard; 34 of 44 up to date, on plan to complete by year end; Need to archive several summer student RAs. GSD/04; Install new Quantum Super Computor (QSC) without injury; Complete, no injuries and 6 learning opportunities raised.; Learning from this installation documented for upgrade planned for next year,. GSD/05; Review QSC building Fire Risk Assessments (FRA) in light of installation.; Complete, actions identified for implementation. |
| Progress with Mandatory Training Other training issues | Progress summarised below: Induction/ Refresher; Fire Safety; Manual Handling; DSE; DSE Self Ass.. % in date; 96%; 80%; 95%; 80%; 78%. Commentary; On track; Awaiting QSC installation and FRA action completion, planned for March 2018; On track; Not on track to mete by FY year end. Director will be speaking to each individual to ensure they realise that this is mandatory.. QSD have a need for a specialist cadmium handling safety course, not currently in the SHE Training Catalogue, would this be of wider interest to RAL Departments? |
| Examples of Departmental successes in SHE management | GSD QSC installation may have learning or others installing major computor hardware. QSD have purchased some simple software to assess EMF hazards, this may be of use for other Departments with these hazards. |  |  |
| Issue of Site wide relevance from Departmental SHE Committee | Recent site emergency exercises had omitted to include within their scope GSD tenants who were not informed of the exercise or asked to respond. It is not clear how to manage the legionella hazards introduced through the QSC cooling management system – this is the only such hazard in QSD – can we utilise another Departments expertise? QSD, since the purchase of the QSC, have a surplus of lone worker alarms handsets should any department need more. |  |  |
| AOB | GSD staff attending the RAL STU have been given appointments in 3 months, can this delay be reduced/made more timely? Can next site exercise include powering down the QSC – this has never been undertaken in an emergency? |  |  |